## Pre-Con Checklist
| MACC IDIQ Contractor Onboarding and Pre-Construction Checklist See the MACC IDIQ Master Contract Sections H and G for more detailed information. Consult with your CO/COR/PO for additional requirements based on the Task Order. | Notes:
See 'NIH ORF Contractor On-Boarding and Construction Requirements' PowerPoint, Environmental Compliance Requirements, and NIH POC List at https://www.orf.od.nih.gov/Construction/Pages/default.aspx *More detailed information is provided on Fire, Security, Safety, Building #10, Environmental Requirements, Badging, Parking, Change Orders and Design Technical Review
CONTRACTOR ONBOARDING Prior to commencement of work the Contractor shall:
H.4 SAFETY* REQUIREMENTS- Go to https://www.ors.od.nih.gov/sr/dohs/YourRole/Pages/Contractor-Safety-Materials.aspx#deliver for all Contractor Safety Requirements which include:
1 | Safety Deliverables - Site Accident Prevention Plan, OSHA Training requirements, Supervisor Safety Orientation, Designation of Contractor Safety/Health Officer and other provisions. Contractor Safety Assessment Program - Go to https://www.constructsecure.com/nih. Contractors and Subcontractors with a low assessment scores, below 80% will be required to address program deficiencies prior to performing work on a MACC Task Order. Contractor Safety Orientation for site supervisors and managers. EM 385-1-1 Army Corps of Engineers Safety and Health Requirements Documents. Joint Commission Requirements for Building #10. Useful Forms, Plans and Checklists.
H.5 SECURITY* REQUIREMENTS
2 | Contractor Security Plan - Submit plan that encompass all administrative, physical, and operational security requirements noted in Section H.5 General, H.5.1. through H.5.4. Communicate with your COR beforehand on what provisions apply. Contractor can draft a general plan for the MACC contract to cover all aspects and amend for task orders as required. Plan shall designate a Security Manager who can also be the Superintendent.
3 | NIH ID Badge* - Each Contractor on the project shall have one of the following NIH ID Badges: - Daily Visitor Badge from the NIH Visitor Center (https://www.nih.gov/about-nih/visitor-information) - Extended Visitor Badge (EVB) badge for non-sensitive duties (Construction Workers, Vendors…). To apply for an EVB badge follow the instructions, forms and procedures provided at https://www.orf.od.nih.gov/Documents/ExtendedVisitorBadgeWF508b.pdf. - Personal Identity Verification (PIV) Badge for direct senior level management (Superintendent, QCM, PM…). PIV badges are limited to those with a continuing and daily need to access the Site and requires COR/PO approval and justification.
4 | Contractor NIH ID Badge Database - Contractors shall maintain a database of all Prime and Subcontractor employees, and others who will perform work or otherwise require access to the site. EVB's are only issued in 6 month intervals and the badging process takes at least 30 days.
Clinical Center Complex (CCC) – All contractor personnel must enter the CCC through the Single Point of Entry (SPE) in Room B2A17A at the B-2 loading dock. An identification badge and proof of receipt of ORFDO’s JC training is required prior to entrance being granted to the CCC.
5 | H.5 PHYSICAL SECURITY* - See NIH Security for Permit for Powder Activated Tools and Fasteners; Construction Task Orders affecting Security Systems; and Projects containing Sensitive Information.
6 | H.6.12 PARKING/TRAFFIC* MITIGATION PLAN - Prime Contractor shall prepare and submit to the COR for approval a Parking/Traffic Plan.
7 | H.11 CONTRACTOR QUALITY CONTROL (CQC) PROGRAM – Provide two copies of the complete CQC Program to the Contracting Officer for review and approval within thirty days after award.
8 | H.16.2 CONSTRUCTION SCHEDULE - Within ten (10) calendar days of receipt of the Notice to Proceed, or within the time set forth in the project specifications, the Contractor shall submit a proposed construction schedule for review and approval by the COR and CO. The construction schedule shall be approved in writing by the COR and CO before any site work is started.
PRE-CONSTRUCTION MEETING
Construction Administration*:
9 | Sign-in and Introductions.
10 | Contractor Organizational Chart - The Contractor shall provide an updated Organizational Chart with full names, titles, mailing and office addresses, phone numbers, e-mails. Clarify who has what authority and the limits of that authority. Firm Principle, Project Manager and Superintendent must be specifically identified. Identify those to be contacted in event of emergencies outside the regular hours of work. Similar information shall be furnished concerning all subcontractors.
11 | Contractor verification of Certificate of Insurance and Bonding.
12 | Schedule - Review Project Schedule and Milestones.
Change Orders*:
13 | Any request for time extensions must be included in the proposed change order.
14 | Requests for delay and impact costs that are not submitted within 60 days after completion of the work identified in the change will not be considered.
15 | See Section G.16.1.6 for Change Orders below $500,000 - allowable percentages for Profit and Overhead.
16 | Track authorized and potential Change Orders with COR/PO using PCO Form.
17 | "Only a warranted Contracting Officer (CO) acting within their delegated limits, has the authority to issue modifications or otherwise change the terms and conditions of the MACC and subsequently issued TOs. If an individual other than the Contracting Officer attempts to make changes to the terms and conditions of the MACC or subsequently issued TOs, the contractor is hereby directed not to proceed with the change and immediately notify the Contracting Officer."
G.15 Invoice Submission and Reporting Requirements:
18 | See Section G.15 for further details, supporting documentation and processing information. No paymentfor non-conforming work. Invoices submitted to: a. The original invoice shall be submitted to the following designated billing office: National Institutes of Health Office of Financial Management Commercial Accounts 2115 East Jefferson Street, Room 4B-432, MSC 8500 Bethesda, MD 20892-8500 b. One copy shall be sent via e-mail as set forth below...
AS APPLICABLE to TASK ORDER
19 | NIH Clinical Center Complex (Building #10)* - ILSM, CRA, OHPE, Fire Marshall, Joint Commission Training.
20 | NIH Design Requirements Manual (DRM)* and Design Review Process. Access to DTR Permit Review Site
21 | Role of IC POC - coordinate access to spaces, Locks, CIT, HM, Telephone, LAN, Locksmithing, Signage, Furniture, Punch lists, Post Construction activities. See IC Checklist at https://www.orf.od.nih.gov/Documents/ICGuidetoDesignandConstructioWorkflow508.pdf
22 | Review process if contractor identifies unforeseen Environmental Hazards during construction.
23 | Review Material Delivery, Storage Areas and Debris Removal.
24 | Review 'After Hours Work Authorization' - Police Department approval required.
25 | Review Fire Protection* - Design Review, Construction Inspection, Fire Protection Services, Building #10 Complex, Hot Work Permits and Extinguishers.
26 | Reporting Fires (Dial 116 or 496-2372).
27 | Environmental Compliance Requirements* See link provided at top of this Checklist.
28 | Work constraints – Hours, noise, dust/flying debris and trafficking through the adjacent facility. Elevators, Cranes, fueled compressors, power tools, Utility Shutdowns, Dumpster Program, Non-Smoking Campus, Trailers, Road Closures, laydown areas, Above Ceiling Permit (Building #10)
29 | Contractor review Section H.6.14 SANITATION AND FOOD SERVICES
30 | Contractor will be responsible for documenting (photo, video, instrument readings, etc.) existing condition such as ambient sound levels (especially in work areas adjacent to occupied spaces), wall and floor finishes, elevator, ceilings, HVAC, mechanical, electrical and plumbing equipment and lines.
PRE - CONSTRUCTION - Other Important Review Items
31 | Bi-Weekly Progress Meetings (or as decided) - COR/PO, IC POC, Contractor and relevant Subcontractors. The Contractor will report at progress meetings with an agenda and provide meeting minutes. All decisions and actions shall be documented by the Contractor via meeting minutes, RFIs, submittals and written correspondence as appropriate.
32 | G.14 CPARS (Contractor Performance Assessment Reporting System). A final evaluation of the Contractor's performance shall be evaluated upon completion of each Task Order valued at more than $700,000. In addition to the final evaluation, interim evaluation(s) will be prepared annually as applicable and additionally as determined to be in the best interest of the Government.
33 | Closeout - Record Documents, As-Builts, O&M Manuals, Training/ User Manual, Warranties/Guarantees Consolidated List, and Project Description/Construction Cost Data.(C.7.4)
34 | Discuss Equipment* Naming convention, Numbering and Tagging Process with COR/PO and Division of Facility Maintenance (DFOM) POC.
35 | Discuss Submittal and Shop Drawing review process with COR/PO.
36 | Renovation work in laboratory areas cannot start until the work area has been certified by the ORS Division of Safety as being clear of any hazardous material.
37 | Mold Discovery, Prevention and Remediation in NIH Owned Facilities – the Contractor shall immediately notify the COR/PO if they discover a water leak or mold regardless of the cause. The COR/PO will notify DOHS, ORS, the ICO, Facility Manager and follow the ORF SOP for remediation as applicable.
38 | Contractor is to maintain Shop Vacuums at work areas in the event of a flood, other water leaks or spillage to prevent further water damage. In addition, contractors shall have a Fire Sprinkler Shut off tool on hand in the event work involves live sprinkler heads (H.4.13.k). Contractor should make every effort to ascertain the location of utility shut off valves and breakers before starting work.
Key Points of Contact
Fire Paul Richards paul.richards@nih.gov 301-496-0487
Physical Security Larry Beverly beverlyl@ors.od.nih.gov 301-827-4517
Safety Jim Ganz james.ganz@nih.gov 301-496-3353
Environmental Mark Miller millermf@mail.nih.gov 301-496-3537
Extended Visitor Badging (EVB) Tim Biggins tim.biggins@nih.gov 301-827-3773
DTR Steve Breslin steven.breslin@nih.gov 301-451-6290
DFOM Equipment Mgmt. Kylash Ramesh kylash.ramesh@nih.gov 301-451-6682
MACC Pete Miller pete.miller@nih.gov 301-451-8464
MACC COR LCDR James Earl james.earl@nih.gov 301-402-9243